## ProductBacklog
< | Priority | User story | Status | Story Points | Missä sprintissä? | Acceptance criteria | RIIPPUVUUDET
1 | 1 | Järjestelmässä näkyy tuotteen nimi | done |  | 1
2 | 1 | Järjestelmässä näkyy kierrätysohje | done |  | 1
3 | 1 | Järjestelmässä näkyy lista tuotteista | done |  | 1
9 | 2 | Käyttäjä voi lisätä tuotteen järjestelmään | done |  | 3
10 | 2 | Käyttäjä voi lisätä tuotteelle kierrätysohjeen | done |  | 3
4 | 3 | Käyttäjä voi hakea tuotetta nimellä | done |  | 3
13 | 3 | Käyttäjä voi luoda käyttäjätunnuksen järjestelmään | done |  | 3 |  | 27
27 | 4 | Käyttäjä voi kirjautua järjestelmään | done |  | 4 |  | 13
24 |  | Kierrätysohje näkyy tuotteen sivulla | done
23 | 4 | Käyttäjä voi täpätä/merkata omat suosituimmat tuotteet | done |  | 5 |  | 15
26 | 4 | Helppo käytettävyys (käyttöliittymän suunnittelu) | done |  | 5 |  | 8, 29
15 | 5 | Käyttäjällä voi olla omat perustuotteet näkymässä | done |  | 5 |  | 23, 30 | vanhempi voi lisätä lapselleen kierrätettäviä tuotteita muistiin.
11 | 999 | Käyttäjä voi äänestä tuotteen kierrätysohjetta | done |  | 6 |  | 18
32 |  | Kierrätysohjeet näytetään järjestyksessä tykkäysten mukaan | done |  | 6 |  | 11
25 | <999 | Kierrätysohjeiden jakaminen
28 | <999 | Kierrätystapahtumamittari |  |  |  |  | 37
29 |  | käyttäjä ohjeistus (help toiminto käyttöliittymään) |  |  |  |  | 26
5 | 999 | Käyttäjä voi hakea tuotetta ean-koodilla |  |  |  |  | 16
6 | 999 | Käyttäjä löytää tuotteelle sopivan lajittelutavan
7 | 999 | Käyttäjä löytää lähimmän sopivan jätteenlajittelupisteen |  |  |  |  | 17, 36
8 | 999 | Käyttäjä voi käyttää sovellusta järjestelmästä huolimatta |  |  |  |  | 26
12 | 999 | Käyttäjä voi kommentoida ohjetta |  |  |  |  | 19
14 | 999 | Käyttäjä voi lisätä omia tietojaan järjestelmään |  |  |  |  | 13, 27
16 | 999 | Järjestelmässä näkyy tuotteen ean koodi |  |  |  |  | 5
17 | 999 | Järjestelmässä näkyy kierrätyspiste |  |  |  |  | 7, 36
18 | 999 | Järjestelmässä näkyy kierrätysohjeen äänet |  |  |  |  | 11
19 | 999 | Järjestelmässä näkyy kierrätysohjeeseen liittyvät kommentit |  |  |  |  | 12
20 | 999 | Käyttäjä voi lisätä tuotteelle kategorian
21 | 999 | Käyttäjä voi lisätä tuotteen kuvan |  |  |  |  | 22
22 | 999 | Tuotteen kuva näkyy järjestelmässä |  |  |  |  | 21
30 |  | yhdellä käyttäjällä voi olla monta näkymää (vanhemman ja lapsen näkymä) |  |  |  |  | 15
31 |  | Käyttäjä voi hakea tuotteet joilla ei ole kierrätysohjettta
33 |  | "Kierrätyskolmio" koodin perusteella
34 |  | Kierrätys ohjeen lisäys lomakkeen muotoilu
35 |  | Nappi joka vie etusivulle muilta sivuilta
36 | 999 | Lähimpien lajittelu/kierrätyspisteiden sijainti karttakuvana |  |  |  |  | 7, 17
37 | 999 | Käyttäjän kierrätystilasto/historia |  |  |  |  | 28
38 | 999 | Kotitalouden kierrätysaste |  |  |  |  | 37
39 |  | Tuotteiden poistaminen |  |  | next?
40 |  | Ohjeiden poistaminen |  |  | next?
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: niko lisää sarakkeen tähän id:tä varten
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lisäsin tämän sarakkeen.
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tämä liittyy kohtaan B2.
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nämä olisivat mielestäni seuraavat yo. prioriteetin 1 (A2:A4) jälkeen. (Tähän taulukkoon olisi muuten hyvä lisätä jokin tarinoiden ID.)
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On hyvä pitää mielessä myös se, että useammalla tuotteella (esim. eri valmistajien "maitopurkit") saattaa olla sama lajitteluohje.
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EHDOTUS
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mikä on "tuotteen sivu"?
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EHDOTUS
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tämä liittyy kohtaan A10. Reply: HUOM! Tuolloin ei ollut ID-saraketta.
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mitä "ohjetta"?
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: esim. taloyhtiössä
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tämä voisi olla esimerkiksi käyttäjän "naputeltava" laskuri siten, että aina tietyn tuotteen lajitellessaan kierrätykseen käyttäjä voisi kirjata sen laskuriinsa.
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mitä tarkoittaa tässä "löytäminen"?
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mitkä "pisteet"?
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mikä on tässä "kategoria"?
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tämä liittyy kohtaan A10, mutta on "nice to have". Aluksi riittäisi hyvin esimerkiksi tuotteen (tai siis yleisemmin kierrätettävän objektin) nimi tms. tekstinä.
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tämä liittyy kohtaan B2.
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tämä voisi olla eri skaaloissa (esim. asunto-osakeyhtiön "jätekatoksista" kunnallisiin ongelmajäteasemiin).
Note on C38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tällainen voi kannustaa parantamaan kierrätysastetta!